## OKR Summary
MotionVii SAAP 2026 — OKR Summary
Strategic Annual Action Plan — Objectives & Key Results
Obj # | Objective | KR # | Key Result | Target | Actual | Unit | Deadline | Progress % | Status | Owner
1 | Scale Events Business | KR1.1 | Submit 7 event proposals by Q4 2026 | 7 | 0 | proposals | Q4 2026 | 0.0% | Not Started | Azlan
|  | KR1.2 | Develop 3 new event partnerships by Q4 2026 | 3 | 0 | partnerships | Q4 2026 | 0.0% | Not Started | Azlan
|  | KR1.3 | Revenue from events is 60% of total by Q4 2026 | 60 | 0 | % | Q4 2026 | 0.0% | Not Started | Khairul
2 | Expand to International B2B Video Market | KR2.1 | Develop lead capture system by Q1 2026 | 1 | 0 | system | Q1 2026 | 0.0% | Not Started | Azlan
|  | KR2.2 | Acquire first international client by Q2 2026 | 1 | 0 | client | Q2 2026 | 0.0% | Not Started | Khairul
|  | KR2.3 | Achieve 5% of revenue from international clients by Q4 2026 | 5 | 0 | % | Q4 2026 | 0.0% | Not Started | Khairul
3 | Develop an A.I-Based Product | KR3.1 | Identify 3 ideas aligned with company capabilities by Q1 2026 | 3 | 0 | ideas | Q1 2026 | 0.0% | Not Started | Azlan
|  | KR3.2 | Join 1 accelerator program by Q2 2026 | 1 | 0 | program | Q2 2026 | 0.0% | Not Started | Khairul
|  | KR3.3 | Secure 1 potential investor by Q4 2026 | 1 | 0 | investor | Q4 2026 | 0.0% | Not Started | Khairul

## Key Results
Key Results — Detailed Tracking
KR ID | Objective | Key Result Description | Metric Type | Target | Actual | Unit | Progress % | Deadline | Status | Owner | How We Measure | Notes
KR1.1 | Scale Events Business | Submit 7 event proposals by Q4 2026 | Count | 7 | 0 | proposals | 0% | Q4 2026 | Not Started | Azlan | Count of proposals submitted (tracked in CRM pipeline)
KR1.2 | Scale Events Business | Develop 3 new event partnerships by Q4 2026 | Count | 3 | 0 | partnerships | 0% | Q4 2026 | Not Started | Azlan | Signed partnership agreements or MOUs
KR1.3 | Scale Events Business | Revenue from events is 60% of total by Q4 2026 | Percentage | 60 | 0 | % | 0% | Q4 2026 | Not Started | Khairul | Event revenue / total revenue from project financials
KR2.1 | Expand International B2B | Develop lead capture system by Q1 2026 | Milestone | 1 | 0 | system | 0% | Q1 2026 | Not Started | Azlan | Website + 3 automation tools + 3 form variants + 3 landing pages live
KR2.2 | Expand International B2B | Acquire first international client by Q2 2026 | Count | 1 | 0 | client | 0% | Q2 2026 | Not Started | Khairul | Signed contract with non-Malaysian client
KR2.3 | Expand International B2B | Achieve 5% revenue from international clients by Q4 2026 | Percentage | 5 | 0 | % | 0% | Q4 2026 | Not Started | Khairul | International project revenue / total revenue
KR3.1 | Develop A.I Product | Identify 3 ideas aligned with capabilities by Q1 2026 | Count | 3 | 0 | ideas | 0% | Q1 2026 | Not Started | Azlan | Documented ideas with feasibility assessment
KR3.2 | Develop A.I Product | Join 1 accelerator program by Q2 2026 | Milestone | 1 | 0 | program | 0% | Q2 2026 | Not Started | Khairul | Accepted and actively participating in accelerator
KR3.3 | Develop A.I Product | Secure 1 potential investor by Q4 2026 | Milestone | 1 | 0 | investor | 0% | Q4 2026 | Not Started | Khairul | Signed term sheet or LOI from investor

## Initiatives
Initiatives — Action Items
ID | KR | Objective | Initiative | Department | Start Date | End Date | Budget (RM) | Resources | Person In Charge | Accountable | Status | Progress | Remarks
1 | KR1.1 | Scale Events | Identify 15 clients to promote event | Operations | 2025-01-01 | 2025-02-28 |  |  | Azlan | Khairul | Pending
2 | KR1.1 | Scale Events | Submit 7 event proposals and set discussions | Operations | 2025-01-01 | 2025-05-31 | 1400 | Meetings | Azlan | Khairul | Pending
3 | KR1.1 | Scale Events | Follow-up with potential clients for events | Operations | 2025-01-01 | 2025-05-31 |  |  | Khairul | Khairul | Pending
4 | KR1.1 | Scale Events | Implement CRM system to track proposals and follow-ups | Operations | 2025-01-01 | 2025-05-31 | 1800 | Software - Pipeline | Khairul | Khairul | Pending
5 | KR1.1 | Scale Events | Conduct discussion on SUKMA 2026 with Bisabi Sdn Bhd | Business Dev | 2025-01-01 | 2025-02-15 |  |  | Khairul | Khairul | Pending
6 | KR1.2 | Scale Events | Source 2 event organisers (not logistics) | Business Dev | 2025-01-01 | 2025-03-31 |  |  | Azlan | Khairul | Pending
7 | KR1.2 | Scale Events | Set meeting with 2 event organisers | Business Dev | 2025-01-01 | 2025-03-31 |  |  | Azlan | Khairul | Pending
8 | KR1.2 | Scale Events | Obtain pricing for 2 other event logistic companies | Business Dev | 2025-06-01 |  |  |  | Azlan | Khairul | Pending
9 | KR1.2 | Scale Events | Secure 2 reliable event PIC/Account manager (freelance/contract) | Business Dev | 2025-01-01 | 2025-06-30 | 60000 | Event manager contract | Khairul | Khairul | Pending
10 | KR1.2 | Scale Events | Attend 1 event organiser exhibition | Business Dev | 2025-06-01 | 2025-12-31 | 2000 | Delegate | Khairul | Khairul | Pending
11 | KR1.3 | Scale Events | Secure 2 events by Q2 2026 | Business Dev | 2025-02-01 | 2025-06-30 |  |  | Khairul | Khairul | Pending
12 | KR1.3 | Scale Events | Secure 4 events by Q4 2026 | Business Dev | 2025-07-01 | 2025-12-31 |  |  | Khairul | Khairul | Pending
13 | KR2.1 | International B2B | Complete MotionVii website | Operations | 2025-01-01 | 2025-02-28 | 4000 | Web Developer | Azlan | Khairul | Pending
14 | KR2.1 | International B2B | Integrate 3 marketing automation tools for lead nurturing | Marketing | 2025-03-01 | 2025-03-31 | 3600 | Automation Tools | Azlan | Khairul | Pending
15 | KR2.1 | International B2B | Test 3 different form structures to improve lead quality | Marketing | 2025-04-01 | 2025-04-30 |  |  | Azlan | Khairul | Pending
16 | KR2.1 | International B2B | Create 3 B2B landing pages with whitepapers & executive briefs | Marketing | 2025-05-01 | 2025-05-31 |  |  | Azlan | Khairul | Pending
17 | KR2.2 | International B2B | Attend 1 international exhibition as participant | Business Dev | 2025-01-01 | 2025-12-31 | 10000 | Travel costs | Khairul | Khairul | Pending
18 | KR2.2 | International B2B | Create 1 marketing pack for video | Marketing | 2025-01-19 | 2025-04-30 |  |  | Azlan | Khairul | Pending
19 | KR2.2 | International B2B | Follow-up with leads from ADIPEC | Business Dev | 2025-01-15 | 2025-02-15 |  |  | Khairul | Khairul | Pending
20 | KR2.2 | International B2B | Follow-up with PETRONAS Abu Dhabi on content localisation | Business Dev | 2025-01-15 | 2025-02-15 |  |  | Khairul | Khairul | Pending
21 | KR2.2 | International B2B | Offer 10sec pilot to 3 potential corporate clients | Operations | 2025-01-26 | 2025-03-31 |  |  | Khairul | Khairul | Pending
22 | KR2.2 | International B2B | Secure 1 freelance/contract for marketing to UAE | HR | 2025-02-01 | 2025-06-30 | 12000 | Marketing person | Khairul | Khairul | Pending
23 | KR2.2 | International B2B | Build 1 portfolio leveraging current partnership | Business Dev | 2025-02-01 | 2025-06-30 |  |  | Azlan | Khairul | Pending
24 | KR2.3 | International B2B | Secure 1 video from international client | Business Dev | 2025-02-01 | 2025-12-31 |  |  | Khairul | Khairul | Pending
25 | KR3.1 | A.I Product | Research 3 possible niche-AI apps that can be developed | Business Dev | 2025-01-01 | 2025-01-31 |  |  | Azlan | Khairul | Pending
26 | KR3.2 | A.I Product | Identify 3 start-up accelerator programs to attend | Business Dev | 2025-02-01 | 2025-02-28 |  |  | Azlan | Khairul | Pending
27 | KR3.2 | A.I Product | Register for 1 start-up accelerator program | Operations | 2025-03-01 | 2025-06-30 |  |  | Azlan | Khairul | Pending
28 | KR3.2 | A.I Product | Participate in 1 start-up accelerator program | Business Dev | 2025-04-01 | 2025-08-31 |  |  | Khairul | Khairul | Pending
29 | KR3.3 | A.I Product | Develop 1 Minimum Viable Product (MVP) | Operations | 2025-04-01 | 2025-11-30 | 25000 | AI-product developer | Khairul | Khairul | Pending
30 | KR3.3 | A.I Product | Present MVP to 5 potential investors | Business Dev | 2025-10-01 | 2025-12-31 |  |  | Khairul | Khairul | Pending
31 | KR3.3 | A.I Product | Conduct 2 AI-training sessions | Business Dev | 2025-01-01 | 2025-12-31 |  |  | Khairul | Khairul | Pending
32 | KR3.3 | A.I Product | Secured 1 potential investor | Business Dev | 2025-10-01 | 2025-12-31 |  |  | Khairul | Khairul | Pending

## Structure Guide
OKR Structure Guide
Layer | What It Is | Example | Tracking | Cadence | Who Owns It
Objective | Aspirational direction (qualitative, inspiring) | Scale Events Business | No metric — just direction | Annual | CEO / Leadership
Key Result | Measurable outcome (specific, time-bound) | Submit 7 event proposals by Q4 2026 | Target vs Actual Progress % Status (On Track / At Risk / Behind) | Quarterly review | KR Owner
Initiative | Action item / project that drives a KR | Implement CRM to track proposals and follow-ups | Status (Not Started → Completed) Start/End dates Budget | Weekly / Bi-weekly | Person In Charge
Key Differences from Previous Format:
Change | Before | After | Why
KR tracking | KRs were just text labels | KRs have Target, Actual, Unit, Progress %, Status | KRs ARE the measurable outcomes — they need real data
Monthly objectives | Mixed into initiative rows | Removed (use weekly planning separately) | Keeps strategic view clean; operational details live elsewhere
Structure | Flat table mixing everything | 3 sheets: Summary → KR Details → Initiatives | Each layer has its own purpose and tracking needs
Measurement | Only Status column | KR: Target/Actual/Progress% ¦ Initiative: Status + Progress | Clear accountability at both outcome and action levels
Status Definitions:
Status | Used For | Meaning
Not Started | KR + Initiative | Work hasn't begun yet
On Track | KR only | Progress is on pace to hit target by deadline
At Risk | KR + Initiative | Behind pace — needs attention or course correction
Behind | KR only | Significantly off target — unlikely to achieve without intervention
In Progress | Initiative only | Actively being worked on
On Hold | Initiative only | Paused — waiting on external dependency
Completed | KR + Initiative | Done — target achieved or action completed
Cancelled | Initiative only | No longer needed