## OKR Summary
MotionVii SAAP 2026 — OKR Summary
Strategic Annual Action Plan — Scale Events Business & Launch AI Training Revenue Stream
Revenue Target: |  | RM1,000,000 | Events: RM800,000 (80%) ¦ AI Training: RM200,000 (20%)
Obj # | Objective | KR # | Key Result | Target | Actual | Unit | Deadline | Progress % | Status | Owner
1 | Scale Events Business | KR1.1 | Win 6 event contracts generating RM800K+ combined revenue by Q4 2026 | 800000 | 0 | RM | Q4 2026 | 0.0% | Not Started | Khairul
|  | KR1.2 | Establish 3 active event partnerships each producing at least 1 joint proposal by Q3 2026 | 3 | 0 | active partnerships | Q3 2026 | 0.0% | Not Started | Azlan
|  | KR1.3 | Secure 3 repeat bookings or referrals from existing event clients by Q4 2026 | 3 | 0 | repeat/referred clients | Q4 2026 | 0.0% | Not Started | Khairul
2 | Build AI Training Business | KR2.1 | Deliver 20 paid corporate AI training sessions by Q4 2026 | 20 | 0 | paid sessions | Q4 2026 | 0.0% | Not Started | Khairul
|  | KR2.2 | Generate RM200K in AI training revenue by Q4 2026 | 200000 | 0 | RM | Q4 2026 | 0.0% | Not Started | Khairul
|  | KR2.3 | Secure 5 repeat or referred training clients by Q4 2026 | 5 | 0 | repeat/referred clients | Q4 2026 | 0.0% | Not Started | Khairul

## Key Results
Key Results — Detailed Tracking
KR ID | Objective | Key Result Description | Metric Type | Target | Actual | Unit | Progress % | Deadline | Status | Owner | How We Measure | Notes
KR1.1 | Scale Events Business | Win 6 event contracts generating RM800K+ combined revenue by Q4 2026 | Revenue | 800000 | 0 | RM | 0% | Q4 2026 | Not Started | Khairul | Combined signed event contract value in CRM (stage = WON). ~6 contracts averaging RM130K. Includes domestic and international events. | The old KR was 'submit proposals' (activity). Revenue from signed contracts is the outcome. International event wins also count here.
KR1.2 | Scale Events Business | Establish 3 active event partnerships each producing at least 1 joint proposal by Q3 2026 | Count | 3 | 0 | active partnerships | 0% | Q3 2026 | Not Started | Khairul | Signed MOU/agreement AND at least 1 joint proposal or referral generated. 'Active' = commercially productive, not just signed. | Partnerships multiply reach. International partnerships (e.g. through ADIPEC contacts) count.
KR1.3 | Scale Events Business | Secure 3 repeat bookings or referrals from existing event clients by Q4 2026 | Count | 3 | 0 | repeat/referred clients | 0% | Q4 2026 | Not Started | Khairul | Clients who (a) rebook another event or (b) refer a new client. Tracked in CRM with source attribution. | Retention proves quality. Includes year-end appreciation effort to secure 2027 rebookings.
KR2.1 | Build AI Training Business | Deliver 20 paid corporate AI training sessions by Q4 2026 | Count | 20 | 0 | paid sessions | 0% | Q4 2026 | Not Started | Khairul | Completed paid sessions (half-day or full-day). Free/discounted pilot workshops do NOT count. HRDCorp-claimable sessions count. International clients count. | 20 sessions at ~RM10K avg = RM200K. Pilots (3 planned) are initiatives that validate content, not KR targets.
KR2.2 | Build AI Training Business | Generate RM200K in AI training revenue by Q4 2026 | Revenue | 200000 | 0 | RM | 0% | Q4 2026 | Not Started | Khairul | Total invoiced AI training revenue. HRDCorp-claimable sessions are premium-priced. 20 sessions x RM10K avg = RM200K target. | HRDCorp certification is a critical initiative — corporates can claim costs from their levy, justifying higher pricing.
KR2.3 | Build AI Training Business | Secure 5 repeat or referred training clients by Q4 2026 | Count | 5 | 0 | repeat/referred clients | 0% | Q4 2026 | Not Started | Khairul | Clients who either (a) book a second training session, or (b) were referred by a previous client. Tracked in CRM with source. | Repeat/referral = proof of quality. More sustainable than cold acquisition. NPS tracking feeds into this.

## Initiatives
Initiatives — Action Items
ID | KR | Objective | Initiative | Department | Start Date | End Date | Budget (RM) | Resources | Person In Charge | Accountable | Status | Progress | Remarks
1 | KR1.1 | Scale Events Business | Identify 15 potential event clients from existing network and industry contacts | Operations | 2026-01-01 | 2026-02-28 |  |  | Azlan | Khairul | Pending
2 | KR1.1 | Scale Events Business | Submit 7 event proposals and set client discussions | Operations | 2026-01-01 | 2026-06-30 | 1400 | Meetings | Azlan | Khairul | Pending |  | Was KR1.1 in old SAAP — now an initiative. Submitting is the work; winning is the outcome.
3 | KR1.1 | Scale Events Business | Follow-up with potential clients (structured cadence via CRM) | Operations | 2026-01-01 | 2026-09-30 |  |  | Khairul | Khairul | Pending
4 | KR1.1 | Scale Events Business | Implement CRM pipeline to track event proposals, follow-ups, and win/loss | Operations | 2026-01-01 | 2026-03-31 | 1800 | Software - Pipeline | Khairul | Khairul | Pending |  | SAAP can feed data back — track proposal stage, conversion rate
5 | KR1.1 | Scale Events Business | Conduct discussion on SUKMA 2026 opportunities with Bisabi Sdn Bhd | Business Dev | 2026-01-01 | 2026-02-28 |  |  | Khairul | Khairul | Pending
6 | KR1.1 | Scale Events Business | Attend 1 international exhibition (ADIPEC/OTC Asia) to source international event leads | Business Dev | 2026-01-01 | 2026-09-30 | 10000 | Travel + registration | Khairul | Khairul | Pending |  | International folded into events. O&G exhibitions have highest-value leads.
7 | KR1.1 | Scale Events Business | Follow-up with ADIPEC leads and PETRONAS Abu Dhabi on content localisation | Business Dev | 2026-01-15 | 2026-03-31 |  |  | Khairul | Khairul | Pending |  | Warmest international lead — Petronas connection in UAE
8 | KR1.1 | Scale Events Business | Offer pilot engagement or proof-of-concept to 3 international prospects | Operations | 2026-02-01 | 2026-06-30 |  |  | Khairul | Khairul | Pending |  | Low-commitment entry point to demonstrate quality to international market
9 | KR1.2 | Scale Events Business | Source and approach 5 event organisers (not logistics) | Business Dev | 2026-01-01 | 2026-03-31 |  |  | Azlan | Khairul | Pending |  | Need 5 approaches to land 3 active partnerships
10 | KR1.2 | Scale Events Business | Set meetings with top 3 event organisers from sourcing list | Business Dev | 2026-02-01 | 2026-04-30 |  |  | Azlan | Khairul | Pending
11 | KR1.2 | Scale Events Business | Obtain pricing from 2 event logistics companies for partnership bundling | Business Dev | 2026-04-01 | 2026-06-30 |  |  | Azlan | Khairul | Pending
12 | KR1.2 | Scale Events Business | Secure 2 reliable event PIC/Account managers (freelance/contract) | Business Dev | 2026-01-01 | 2026-06-30 | 60000 | Event manager contracts | Khairul | Khairul | Pending
13 | KR1.2 | Scale Events Business | Attend 2 industry events for networking and partnership development | Business Dev | 2026-03-01 | 2026-09-30 | 2000 | Delegate passes | Khairul | Khairul | Pending
14 | KR1.2 | Scale Events Business | Create international marketing pack showcasing Petronas and O&G video portfolio | Marketing | 2026-01-15 | 2026-03-31 |  |  | Azlan | Khairul | Pending |  | Leverage strongest asset to open both domestic and international partnership doors
15 | KR1.3 | Scale Events Business | Build event case studies for marketing (min 2 case studies) | Marketing | 2026-03-01 | 2026-06-30 |  |  | Azlan | Khairul | Pending |  | Case studies drive both repeat bookings and new referrals
16 | KR1.3 | Scale Events Business | Secure repeat bookings from existing clients through proactive outreach | Business Dev | 2026-06-01 | 2026-10-31 |  |  | Khairul | Khairul | Pending
17 | KR1.3 | Scale Events Business | Year-end client appreciation and 2027 planning sessions | Business Dev | 2026-10-01 | 2026-12-31 |  |  | Khairul | Khairul | Pending |  | Lock in 2027 commitments while relationship is warm
18 | KR1.3 | Scale Events Business | Build 1 international portfolio piece leveraging Petronas partnership | Business Dev | 2026-03-01 | 2026-09-30 |  |  | Azlan | Khairul | Pending |  | International credibility piece that feeds both new leads and repeat trust
19 | KR2.1 | Build AI Training Business | Research corporate AI training market, competitors, and pricing in Malaysia | Business Dev | 2026-01-01 | 2026-02-15 |  |  | Azlan | Khairul | Pending |  | What would Petronas/corporate teams actually pay to learn?
20 | KR2.1 | Build AI Training Business | Define 3 AI training modules (topics, duration, pricing) | Business Dev | 2026-01-15 | 2026-02-28 |  |  | Khairul | Khairul | Pending |  | e.g. AI for O&G, AI for Marketing, Generative AI Workflows
21 | KR2.1 | Build AI Training Business | Develop Module 1 curriculum and materials | Operations | 2026-02-01 | 2026-03-31 | 5000 | Content development | Khairul | Khairul | Pending
22 | KR2.1 | Build AI Training Business | Develop Module 2 curriculum and materials | Operations | 2026-03-01 | 2026-04-30 | 5000 | Content development | Khairul | Khairul | Pending
23 | KR2.1 | Build AI Training Business | Develop Module 3 curriculum and materials | Operations | 2026-04-01 | 2026-05-31 | 5000 | Content development | Khairul | Khairul | Pending
24 | KR2.1 | Build AI Training Business | Conduct 3 pilot workshops (discounted/free) to validate content and delivery | Operations | 2026-03-01 | 2026-05-31 |  |  | Khairul | Khairul | Pending |  | Pilots do NOT count toward KR2.1 (paid sessions). They validate content and generate testimonials.
25 | KR2.1 | Build AI Training Business | Refine curriculum based on pilot feedback | Operations | 2026-05-01 | 2026-06-30 |  |  | Khairul | Khairul | Pending |  | Iterate before commercial launch — critical quality gate
26 | KR2.2 | Build AI Training Business | Apply for HRDCorp training provider certification | Business Dev | 2026-01-15 | 2026-04-30 |  |  | Khairul | Khairul | Pending |  | CRITICAL: HRDCorp certification lets corporates claim training costs from levy. Major selling point in Malaysia.
27 | KR2.2 | Build AI Training Business | Price and package training offerings (half-day, full-day, multi-session series) | Operations | 2026-02-01 | 2026-03-31 |  |  | Khairul | Khairul | Pending |  | Target RM10K+ per corporate session. HRDCorp-claimable sessions priced at premium.
28 | KR2.2 | Build AI Training Business | Identify 20 target companies for AI training (leverage Petronas network) | Business Dev | 2026-02-01 | 2026-04-30 |  |  | Azlan | Khairul | Pending |  | Start with warm leads — companies that already know MotionVii or Petronas ecosystem
29 | KR2.2 | Build AI Training Business | Create AI Training marketing collateral (brochure, website section) | Marketing | 2026-03-01 | 2026-05-31 | 3000 | Design + web | Azlan | Khairul | Pending
30 | KR2.2 | Build AI Training Business | Launch full commercial AI training offering | Marketing | 2026-05-01 | 2026-06-30 |  |  | Khairul | Khairul | Pending |  | After pilots are validated and HRDCorp cert is in progress
31 | KR2.2 | Build AI Training Business | Pitch AI training to top 10 corporate prospects | Business Dev | 2026-04-01 | 2026-07-31 |  |  | Khairul | Khairul | Pending
32 | KR2.2 | Build AI Training Business | Deliver 20 corporate workshop sessions | Operations | 2026-05-01 | 2026-12-31 |  |  | Khairul | Khairul | Pending |  | Main delivery effort — ramp up after commercial launch
33 | KR2.2 | Build AI Training Business | Explore AI training opportunities with international corporates (e.g. Petronas Abu Dhabi) | Business Dev | 2026-06-01 | 2026-12-31 |  |  | Khairul | Khairul | Pending |  | International folded in — international training revenue also counts toward 20%
34 | KR2.3 | Build AI Training Business | Implement post-training feedback survey and NPS tracking | Operations | 2026-04-01 | 2026-05-31 |  |  | Azlan | Khairul | Pending |  | Data to prove quality, identify improvements, and support testimonials
35 | KR2.3 | Build AI Training Business | Create AI training case study and testimonials from first sessions | Marketing | 2026-06-01 | 2026-08-31 |  |  | Azlan | Khairul | Pending |  | Social proof drives referrals — get permission from pilot participants
36 | KR2.3 | Build AI Training Business | Follow up with all trained participants about advanced sessions and referrals | Business Dev | 2026-07-01 | 2026-12-31 |  |  | Khairul | Khairul | Pending |  | Systematic — don't rely on organic referrals. Schedule follow-ups in CRM.
37 | KR2.3 | Build AI Training Business | Offer referral incentive (discount on next session) to existing training clients | Marketing | 2026-06-01 | 2026-12-31 |  |  | Azlan | Khairul | Pending

## Structure Guide
OKR Structure Guide
Layer | What It Is | Example | Tracking | Review Cadence | Who Owns It
Objective | Aspirational direction (qualitative, inspiring) 2 objectives for 2026: 80% Events + 20% AI Training | Scale Events Business | No metric — just direction. Success = KRs achieved. | Annual | CEO / Leadership
Key Result | Measurable OUTCOME (specific, time-bound) Must answer: 'What changed?' NOT: 'What did we do?' | Win 6 event contracts generating RM800K+ by Q4 | Target vs Actual Progress % Status (On Track / At Risk) | Monthly review Quarterly scoring | KR Owner
Initiative | Action item that DRIVES a KR This is the work you do. Multiple initiatives per KR. | Submit 7 event proposals and set discussions | Status (Pending → Completed) Start/End dates, Budget | Weekly / Bi-weekly | Person In Charge
Revenue Target Breakdown:
Stream | Target | % of Total | Key Revenue Logic
Events | RM800,000 | 80% | ~6 events x RM130K avg. Includes domestic + international.
AI Training | RM200,000 | 20% | ~20 sessions x RM10K avg. HRDCorp-claimable = premium pricing.
Total | RM1,000,000 | 100% | International revenue counts under whichever stream it falls.
What Changed from Previous SAAP:
Change | Before | After | Why
3 → 2 Objectives | Events + International B2B + AI Product (3 separate) | Events (80%) + AI Training (20%) International folded into both | International is a market strategy, not a business line. Revenue counts under events or training.
AI Product → Training | Build product, join accelerator, find investor | Deliver paid training to corporates, generate RM200K, earn repeat clients | Training leverages existing expertise and client base (Petronas network). No investor needed — revenue model.
KR = Outcome | 'Submit 7 proposals' (activity) 'Build lead system' (task) | 'Win 6 contracts / RM800K' (outcome) 'Deliver 20 sessions' (outcome) | KRs measure results, not effort. Activities become initiatives.
HRDCorp certification | Not in previous SAAP | Critical initiative under KR2.2 (enables corporate sales) | Corporates claim training costs from HRDCorp levy — major selling point in Malaysian market.
Revenue targets | No explicit revenue numbers on KRs | KR1.1: RM800K ¦ KR2.2: RM200K RM1M total | Revenue makes KRs concrete and ties directly to business goal.
OKR Anti-Patterns to Avoid:
Anti-Pattern | Example | Fix | Diagnostic Test
Activity as KR | 'Submit 7 proposals' | 'Win 4 contracts' | 'Can I do this without the business improving?' If yes → it's an activity.
Task as KR | 'Build lead capture system' | 'Generate 20 qualified leads' | 'Is this a deliverable or a result?' Systems/tools are deliverables.
Vague KR | 'Develop 3 partnerships' | '3 active partnerships each producing 1+ joint proposal' | 'Would two people agree this is achieved?' Add qualifying criteria.

## Support Tasks
Support Tasks — Operational Work Supporting SAAP Initiatives
These are recurring, ad-hoc, or BAU tasks — not strategic initiatives, but needed to deliver them.
ID | Category | Task | Supports | Owner | Frequency | Priority | Notes
1 | Design & Creative | Design event proposal decks and pitch materials | KR1.1 | Azlan | Per proposal | High | Each of the 7 proposals needs a tailored deck. Template-first approach to save time.
2 | Design & Creative | Design event collateral (banners, backdrops, signage, badges) | KR1.1 | Azlan | Per event won | High | Triggered after contract signed. Budget included in event project cost.
3 | Design & Creative | Video production and editing for event content | KR1.1, KR1.3 | Azlan | Per event | High | Event recap videos, highlight reels. Also feeds case studies for KR1.3.
4 | Design & Creative | Design event case study layouts | KR1.3 | Azlan | 2x per year | Medium | Supports initiative #15 — need min 2 case studies for marketing.
5 | Design & Creative | Design international marketing pack (portfolio, showreel) | KR1.2 | Azlan | Once + updates | High | Supports initiative #14. Showcase Petronas/O&G work for partnerships and intl prospects.
6 | Design & Creative | Update MotionVii website content and visuals | KR1.2, KR2.2 | Azlan | Monthly | Medium | Keep portfolio current. Add AI training section after commercial launch.
7 | Design & Creative | Social media content creation (posts, reels, stories) | KR1.2, KR2.2 | Azlan | Weekly | Medium | Maintain brand visibility across both events and AI training.
8 | Design & Creative | Design AI training presentation slides and handout materials | KR2.1 | Azlan | Per module | High | Supports Module 1/2/3 development. Professional materials = premium pricing justified.
9 | Design & Creative | Design AI training brochure and marketing collateral | KR2.2 | Azlan | Once + updates | High | Supports initiative #29. Needs to be ready before commercial launch.
10 | Design & Creative | Video testimonials from training participants | KR2.3 | Azlan | After each session | Medium | Quick video testimonials boost referral credibility. Get permission during session.
11 | Design & Creative | Portfolio and showreel updates (quarterly refresh) | KR1.1, KR1.2 | Azlan | Quarterly | Medium | Keep demo reel current with latest event and video work.
12 | Business & Admin | Proposal writing and quotation preparation | KR1.1 | Khairul | Per opportunity | High | Each proposal needs custom scope, pricing, timeline. Use templates to speed up.
13 | Business & Admin | Contract preparation, review, and execution | KR1.1, KR2.2 | Khairul | Per deal | High | Both event contracts and AI training contracts.
14 | Business & Admin | Invoicing and payment follow-up | KR1.1, KR2.2 | Khairul | Per project/session | High | Revenue only counts when invoiced. Track in SAAP project financials.
15 | Business & Admin | Financial reporting and budget tracking (SAAP) | All KRs | Khairul | Monthly | High | Monthly review of revenue vs RM1M target. Events vs Training split.
16 | Business & Admin | Client relationship management and meeting notes | KR1.1, KR1.3 | Khairul | Ongoing | Medium | CRM updates after every client interaction. Feed data to KR tracking.
17 | Business & Admin | Supplier and vendor management (logistics, venues, AV) | KR1.1, KR1.2 | Khairul | Per event | Medium | Negotiate rates, manage relationships, ensure delivery quality.
18 | Business & Admin | HR — freelancer/contractor onboarding and management | KR1.2 | Khairul | As needed | Medium | Event PIC managers, marketing contractors. Supports initiative #12.
19 | Business & Admin | HRDCorp application documentation and follow-up | KR2.2 | Khairul | Until approved | High | Supports initiative #26. Documentation-heavy process — track milestones.
20 | Business & Admin | AI training session logistics (venue, equipment, catering) | KR2.1 | Khairul | Per session | Medium | Book venue, arrange equipment, handle logistics for each corporate session.
21 | Business & Admin | Partnership agreement drafting and negotiation | KR1.2 | Khairul | Per partnership | Medium | MOU or formal partnership agreement. Legal review if needed.
22 | Business & Admin | International compliance and logistics (travel, permits, banking) | KR1.1 | Khairul | Per intl engagement | Low | Only triggered when international work materializes. Cross-border invoicing, travel planning.
23 | Talenta Ideas | Design requests from Talenta Ideas (ad-hoc) | Parent company | Azlan | Ad-hoc | Medium | As subsidiary, MotionVii supports Talenta's design needs. Track hours to manage capacity.
24 | Talenta Ideas | Video production requests from Talenta Ideas | Parent company | Azlan | Ad-hoc | Medium | Corporate videos, internal comms, event coverage for Talenta's own projects.
25 | Talenta Ideas | Talenta Ideas brand and marketing material updates | Parent company | Azlan | Quarterly | Low | Brochure updates, presentation templates, brand guideline maintenance.
26 | Talenta Ideas | Coordination and reporting to Talenta Ideas management | Parent company | Khairul | Monthly | Medium | Monthly update on MotionVii performance, revenue, and SAAP progress to parent company.
27 | Operations | SAAP platform maintenance and development | All KRs | Khairul | Ongoing | Medium | The tool tracking all of this. Bug fixes, new features, data integrity.
28 | Operations | Software subscriptions and tool management | All KRs | Khairul | Monthly | Low | CRM, automation tools, design software, project management. Renewals and cost control.
29 | Operations | Document management and filing (contracts, proposals, invoices) | All KRs | Khairul | Ongoing | Low | Keep organized for audits, HRDCorp requirements, and client records.
30 | Operations | Team capacity planning and workload balancing | All KRs | Khairul | Bi-weekly | High | 3-person team running 37 initiatives + support tasks + Talenta requests. Watch for bottlenecks on Azlan (design) and Khairul (business).