## SAAP
THE STRATEGIC ACTION PLAN (SAAP) 2026
MOTIONVII SDN BHD
Strategic Objective: |  |  | Scale Events Business & Launch AI Training Revenue Stream
Revenue Target: |  |  | RM1,000,000 | Events: RM800,000 (80%) |  | AI Training: RM200,000 (20%)
ID | Objective | Key Result | Department | Initiative | Monthly Objective | Weekly Tasks | Start Date | End Date | Resources (Financial) | Resources (Non-Financial) | Person In Charge | Accountable | Status | Remarks
1 | Obj 1: Scale Events | KR1.1 | Biz Dev | Review 2025 event client performance and identify upsell opportunities | Complete client review | Analyze revenue, margins, feedback | 2026-01-01 | 2026-01-31 |  |  | Khairul | Khairul | Pending
2 | Obj 1: Scale Events | KR1.1 | Biz Dev | Schedule Q1 relationship meetings with top 5 clients | 5 meetings scheduled | Outreach, calendar booking | 2026-01-01 | 2026-02-28 |  |  | Khairul | Khairul | Pending
3 | Obj 1: Scale Events | KR1.2 | Operations | Develop 2026 event proposal templates | Templates ready | Design, content, pricing | 2026-01-01 | 2026-01-31 |  | Design software | Azlan | Khairul | Pending
4 | Obj 1: Scale Events | KR1.2 | Biz Dev | Identify 10 target prospects for new client acquisition | 10 prospects listed | Research, qualify leads | 2026-01-01 | 2026-01-31 |  | CRM | Khairul | Khairul | Pending
5 | Obj 1: Scale Events | KR1.2 | Biz Dev | Submit proposals to 10 new prospects | 10 proposals sent | Customize, submit, track | 2026-02-01 | 2026-03-31 |  |  | Khairul | Khairul | Pending
6 | Obj 1: Scale Events | KR1.2 | Biz Dev | Follow-up and close 5 new event clients | 5 clients signed | Negotiations, contracts | 2026-01-01 | 2026-06-30 |  |  | Khairul | Khairul | Pending
7 | Obj 1: Scale Events | KR1.3 | Operations | Review and optimize supplier/vendor contracts | Contracts reviewed | Negotiate better terms | 2026-02-01 | 2026-02-28 |  |  | Khairul | Khairul | Pending
8 | Obj 1: Scale Events | KR1.3 | Operations | Develop event delivery SOP and checklists | SOP documented | Document processes | 2026-02-01 | 2026-02-28 |  |  | Azlan | Khairul | Pending
9 | Obj 1: Scale Events | KR1.1 | Operations | Create post-event portfolio updates after each event | Portfolio updated | Photos, videos, case study | 2026-01-01 | 2026-12-31 |  | Design software | Azlan | Azlan | Pending | Ongoing
10 | Obj 1: Scale Events | KR1.3 | Finance | Implement event cost tracking system | System implemented | Setup, train team | 2026-03-01 | 2026-03-31 |  | Spreadsheet/software | Izyani | Khairul | Pending
11 | Obj 1: Scale Events | KR1.1 | Biz Dev | Conduct quarterly event performance reviews | 4 reviews completed | Analyze metrics, adjust | 2026-01-01 | 2026-12-31 |  |  | Khairul | Khairul | Pending | Quarterly
12 | Obj 1: Scale Events | KR1.2 | Marketing | Build event case studies for marketing | 3 case studies | Write, design, publish | 2026-04-01 | 2026-06-30 |  |  | Azlan | Khairul | Pending
13 | Obj 1: Scale Events | KR1.2 | Biz Dev | Attend 2 industry events for networking | 2 events attended | Register, attend, follow-up | 2026-04-01 | 2026-09-30 | RM3,000 | Travel, registration | Khairul | Khairul | Pending
14 | Obj 1: Scale Events | KR1.2 | Biz Dev | Develop partnership with 2 event organizers | 2 partnerships signed | Identify, meet, negotiate | 2026-04-01 | 2026-06-30 |  |  | Khairul | Khairul | Pending
15 | Obj 1: Scale Events | KR1.1 | Biz Dev | Secure repeat bookings from existing clients | 80% retention | Relationship management | 2026-07-01 | 2026-12-31 |  |  | Khairul | Khairul | Pending
16 | Obj 1: Scale Events | KR1.1 | Biz Dev | Year-end client appreciation and 2027 planning | Event completed | Plan, execute, collect feedback | 2026-12-01 | 2026-12-31 | RM2,000 |  | Khairul | Khairul | Pending
17 | Obj 2: AI Training | KR2.1 | Biz Dev | Research corporate AI training market and competitors | Research complete | Market analysis, pricing | 2026-01-01 | 2026-01-31 |  |  | Khairul | Khairul | Pending
18 | Obj 2: AI Training | KR2.1 | Biz Dev | Define 3 AI training modules (topics, duration, pricing) | 3 modules defined | Outline curriculum | 2026-01-01 | 2026-01-31 |  |  | Khairul | Khairul | Pending
19 | Obj 2: AI Training | KR2.1 | Operations | Develop Module 1 curriculum and materials | Module 1 ready | Content, slides, exercises | 2026-01-15 | 2026-02-28 | RM5,000 | Design, content tools | Khairul | Khairul | Pending
20 | Obj 2: AI Training | KR2.1 | Operations | Develop Module 2 curriculum and materials | Module 2 ready | Content, slides, exercises | 2026-02-01 | 2026-03-31 | RM5,000 | Design, content tools | Khairul | Khairul | Pending
21 | Obj 2: AI Training | KR2.1 | Operations | Develop Module 3 curriculum and materials | Module 3 ready | Content, slides, exercises | 2026-03-01 | 2026-04-30 | RM5,000 | Design, content tools | Khairul | Khairul | Pending
22 | Obj 2: AI Training | KR2.2 | Biz Dev | Apply for HRDCorp training provider certification | Application submitted | Prepare docs, submit | 2026-02-01 | 2026-02-28 | RM3,000 | Documentation | Khairul | Khairul | Pending
23 | Obj 2: AI Training | KR2.3 | Marketing | Create AI Training marketing collateral (brochure, website) | Materials ready | Design, copywriting | 2026-02-01 | 2026-02-28 | RM3,000 | Design software | Azlan | Khairul | Pending
24 | Obj 2: AI Training | KR2.3 | Biz Dev | Identify 20 target companies for AI training | 20 prospects listed | Research, qualify | 2026-02-01 | 2026-02-28 |  | CRM | Khairul | Khairul | Pending
25 | Obj 2: AI Training | KR2.3 | Operations | Conduct 3 pilot workshops (discounted/free) | 3 pilots completed | Deliver, collect feedback | 2026-03-01 | 2026-04-30 | RM2,000 | Venue, materials | Khairul | Khairul | Pending
26 | Obj 2: AI Training | KR2.1 | Operations | Refine curriculum based on pilot feedback | Curriculum updated | Incorporate feedback | 2026-04-01 | 2026-04-30 |  |  | Khairul | Khairul | Pending
27 | Obj 2: AI Training | KR2.3 | Marketing | Launch full commercial AI training offering | Launch completed | Marketing push, sales | 2026-05-01 | 2026-05-31 | RM2,000 | Marketing channels | Khairul | Khairul | Pending
28 | Obj 2: AI Training | KR2.3 | Operations | Deliver 20 corporate workshop sessions | 20 sessions delivered | Schedule, deliver, invoice | 2026-05-01 | 2026-12-31 |  | Venues, materials | Khairul | Khairul | Pending | Target: RM200K revenue

## Events to Attend
EVENTS TO ATTEND 2026 - MOTIONVII
Total: 38 Events ¦ Tier 1: 10 ¦ Tier 2: 10 ¦ Tier 3: 8 ¦ Energy: 10
Priority | Event Name | Category | Date | Location | Est. Cost | Why Attend | Target Companies | Action Required | Status
Tier 1 | PETRONAS Malaysia Open | Events | Jan 6-11, 2026 | Axiata Arena, Bukit Jalil | RM500 | Major sports event, networking with sponsors | BAM, sports sponsors, media companies | Register as visitor | Planned
Tier 1 | Malaysia Brand Day | Both | Jan 8-10, 2026 | KLCC | RM1,000 | 300+ SMEs, B2B matching with ASEAN buyers | SMEs needing events & training, exporters | Book booth or register | Planned
Tier 1 | Asia AI Infrastructure Summit | AI Training | Feb 11, 2026 | W Hotel KL | RM2,000 | 300+ AI stakeholders, enterprise IT leaders | Data centers, hyperscalers, enterprise IT | Early bird registration | Planned
Tier 1 | Digital Transformation Summit | AI Training | Apr 23, 2026 | Kuala Lumpur | RM2,500 | 500+ C-level execs seeking digital solutions | Fortune 500, government agencies | Register by Mar 2026 | Planned
Tier 1 | HR Tech Asia | AI Training | May 5-6, 2026 | Suntec Singapore | RM4,000 | 1,500+ HR decision-makers with training budgets | MNCs, tech companies, consulting firms | Book flights + register | Planned
Tier 1 | Broadcast Asia | Events | May 20-22, 2026 | Singapore Expo | RM3,500 | Video/media technology, content production | Broadcast networks, streaming platforms | Book flights + register | Planned
Tier 1 | Learning & Development Asia | AI Training | Sept 2026 | Kuala Lumpur | RM2,000 | Direct L&D decision-makers, 11th edition | PETRONAS, Maybank, Maxis, Malaysia Aviation | Watch for dates | Planned
Tier 1 | SUKMA 2026 | Events | Aug 15-24, 2026 | Selangor (31 venues) | RM5,000 | RM250M budget, 10,000 athletes, flagship event | State govt, NSC, universities, sponsors | Contact Selangor govt | Planned
Tier 1 | AI Revolution Summit | AI Training | Sept 22, 2026 | Kuala Lumpur | RM2,000 | 200+ curated AI stakeholders, policy focus | Enterprises, government, policymakers | Register by Aug 2026 | Planned
Tier 1 | NHCCE (HRDCorp) | AI Training | Oct 2026 | MITEC KL | RM2,500 | Largest HR event, 10,000+ visitors | HR leaders, training providers, corporates | Watch for dates | Planned
Tier 2 | Conversational AI Summit | AI Training | Mar 18, 2026 | Kuala Lumpur | RM1,500 | Startup showcase, VC networking | Banks, telcos, e-commerce | Register | Planned
Tier 2 | Thailand MICE Exchange | Events | Apr 29-30, 2026 | Bangkok QSNCC | RM2,200 | 4,000+ MICE delegates, regional expansion | Event organizers, DMCs, hotels | Book flights + register | Planned
Tier 2 | DMAT Confex | Both | Apr 29, 2026 | Kuala Lumpur | RM1,500 | 200+ global leaders, GenAI in marketing | CMOs, agencies, startups | Register | Planned
Tier 2 | GTI Southeast Asia Expo | Events | Apr 21-23, 2026 | WTC KL | RM1,500 | Entertainment/attractions industry | Theme parks, FECs, VR companies | Register | Planned
Tier 2 | Malaysia Business Events Week | Events | May 2026 | MITEC/KLCC | RM1,000 | Flagship MICE industry event | Event suppliers, venues, organizers | Watch for dates | Planned
Tier 2 | MIFFest (Film Festival) | Events | Jul 18-25, 2026 | Kuala Lumpur | RM1,000 | Creative industry visibility | Filmmakers, production studios, broadcasters | Register | Planned
Tier 2 | Tech Week Singapore | AI Training | Sept 29-30, 2026 | Singapore | RM4,000 | 29,000+ business leaders, 5 co-located events | Cloud, AI, cybersecurity companies | Book flights + register | Planned
Tier 2 | MICE Show Asia | Events | Oct 21-23, 2026 | Marina Bay Sands | RM4,500 | Asia's leading MICE trade show | Event organizers, DMCs, corporate planners | Book flights + register | Planned
Tier 2 | What's NEXT in Marketing | Both | Oct 22, 2026 | Kuala Lumpur | RM1,500 | Progressive marketers, AI-driven campaigns | Digital agencies, e-commerce brands | Register | Planned
Tier 2 | 100 CHRO Malaysia | AI Training | 2026 TBD | Kuala Lumpur | RM2,000 | C-suite HR executives, AI transformation | Top 500 companies, CHROs, VP HR | Watch for dates | Planned
Tier 3 | NEF Impact Tech Conference | AI Training | Jan 17, 2026 | APU Bukit Jalil | RM500 | AI predictions for Malaysia | Tech innovators, impact investors | Register | Planned
Tier 3 | Fintech Revolution Summit | AI Training | Jul 23, 2026 | Crowne Plaza KL | RM2,000 | 200+ C-level, AI in banking | Banks, fintech, payment companies | Register | Planned
Tier 3 | KLPJ Wedding Fair | Events | Jan 24-25, 2026 | KLCC | RM1,000 | Wedding industry networking | Wedding planners, venues, vendors | Register | Planned
Tier 3 | DSA (Defence) | Events | Apr 20-23, 2026 | MITEC KL | RM2,000 | Top 5 global defence show | Defence contractors, government | Register | Planned
Tier 3 | Startup Grind Mania | AI Training | Apr 27-29, 2026 | Silicon Valley | RM15,000 | 5,000+ entrepreneurs, global investors | VCs, accelerators, tech startups | Book flights early | Planned
Tier 3 | IAAPA Expo Middle East | Events | Mar 30-Apr 2, 2026 | ADNEC Abu Dhabi | RM5,000 | First IAAPA in Middle East | Theme parks, attractions, entertainment | Book flights + register | Planned
Tier 3 | Solartech Indonesia | Both | Apr 22-24, 2026 | Jakarta | RM3,500 | 35,000 visitors, renewable energy | Solar installers, utilities, storage | Book flights + register | Planned
Tier 3 | Electric & Power Indonesia | Both | Sept 2-5, 2026 | Jakarta | RM4,000 | ASEAN's largest power exhibition | PT PLN, utilities, equipment makers | Book flights + register | Planned
Energy | IPTC Summit (AI in Energy) | Both | Jan 13-14, 2026 | Conrad Dubai | RM4,500 | AI & digital in energy, early UAE entry | Oil majors, NOCs, tech companies | Register early | Planned
Energy | OTC Asia | Events | Mar 31-Apr 2, 2026 | KLCC | RM3,000 | 23,000 attendees, offshore technology | Shell, ExxonMobil, PETRONAS | Register | Planned
Energy | Middle East Energy | Both | Apr 7-9, 2026 | Dubai WTC | RM5,000 | 40+ years, battery & solar co-located | ADNOC, utilities, renewables | Book flights + register | Planned
Energy | GOTECH Dubai | Both | Apr 13-15, 2026 | Dubai WTC | RM4,000 | Innovation summit, startups to majors | Energy tech startups, oil majors | Register | Planned
Energy | Oil & Gas Malaysia | Events | Jun 3-5, 2026 | KLCC | RM2,500 | Major Malaysian exhibition | PETRONAS, Dialog, Sapura | Register | Planned
Energy | Sabah Oil & Gas (SOGCE) | Events | Jun 25-26, 2026 | Kota Kinabalu | RM2,000 | Regional focus, less crowded | Sabah operators, exploration cos | Book flights + register | Planned
Energy | Oil & Gas Asia (OGA) | Both | Sept 2-4, 2026 | KLCC | RM4,000 | 30,000 attendees, 2,000 companies | PETRONAS, Dialog, regional contractors | Register early | Planned
Energy | Enlit Asia | Both | Sept 22-24, 2026 | Singapore/Bangkok | RM4,500 | 11,000 attendees, power utilities | Utilities, data centers, grid operators | Book flights + register | Planned
Energy | Asian Downstream Summit | Both | Oct 28-29, 2026 | Marina Bay Sands | RM4,000 | 1,000+ petrochemical executives | Refineries, petrochemical manufacturers | Book flights + register | Planned
Energy | ADIPEC | Both | Nov 2-5, 2026 | Abu Dhabi | RM8,000 | World's largest energy event, 2,250 exhibitors | All global energy companies | Book early, existing leads | Planned
BUDGET SUMMARY
Tier 1 (10 events) |  |  |  |  | ~RM25,000
Tier 2 (10 events) |  |  |  |  | ~RM20,000
Tier 3 (8 events) |  |  |  |  | ~RM31,000
Energy (10 events) |  |  |  |  | ~RM41,500
TOTAL (38 events) |  |  |  |  | ~RM117,500